## Project Timeline
PROJECT TITLE |  | Florals’ Online Website |  | COMPANY NAME | [6 empty] | DAMCO Solutions
PROJECT MANAGER |  | Musab Khan |  | DATE | [6 empty] | 2024-08-21
PHASE |  |  | DETAILS | Q1 | [12 empty] | Q2
|  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan
| PROJECT WEEK: |  |  | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1 | Project Planning and Initiation |  | Project Planning & Initiation | bar: Sep 2 to Sep 9
Project monitoring & control | bar: Jan 6 to Jan 13
Project closure | bar: Jan 20
2 | Requirement Gathering and Analysis |  | Stakeholder Interviews and Workshops | bar: Sep 9 to Sep 16
Business Requirements Document (BRD) Preparation
Functional and Non-Functional Requirements Gathering | bar: Sep 16 to Sep 23
Requirements Validation and Approval
3 | Design & Architecture |  | Website UI/UX Design | bar: Sep 23 to Oct 7
Backend Architecture Design | bar: Oct 30 to Oct 7
Integration Framework Design | bar: Oct 30
Security Architecture Design
Design Validation and Sign-off | bar: Oct 14 to Oct 21
4 | Development |  | 1. Frontend Development | bar: Oct 7 to Oct 28
Homepage Development
Product Catalog Development
Shopping Cart and Checkout Development
User Profile Management
2. Backend Development | bar: Oct 28 to Nov 18
Database Setup and Configuration
API Development
Payment Gateway Integration
Order Management System
3. Integration | bar: Nov 18 to Nov 25
Legacy System Integration
Third-Party Tool Integration
Analytics Engine Implementation
5 | Testing & Quality Assaurance |  | Unit Testing | bar: Dec 2
System Integration Testing (SIT) | bar: Dec 9 to Dec 16
User Acceptance Testing (UAT) | bar: Dec 16
Performance Testing
Security Testing
6 | Deployement |  | Production Environment Setup | bar: Dec 23
Data Migration
Website Launch | bar: Jan 30
Post-Launch Monitoring and Support | bar: Jan 6 to Jan 13

## Milestone Timeline
S.No. | Milestone | Date | Milestone Number
1 | Project Planning and Initiation Completed | 2024-09-13 | M1
2 | BRD Approved | 2024-09-20 | M2
3 | Design Phase Completed | 2024-10-07 | M3
4 | Frontend Development Completed | 2024-10-28 | M4
5 | Backend Development Completed | 2024-11-18 | M5
6 | System Integrated and Tested | 2024-12-16 | M6
7 | UAT Sign-Off | 2024-12-21 | M7
8 | Website Launched | 2024-12-30 | M8
9 | Project Completion | 2025-01-20 | M9

## RAID
RAID ID | Type | Description | Impact | Probability | Mitigation/Action
R1 | Risk | Legacy system integration might cause compatibility issues | High | Medium | Conduct a thorough technical feasibility study and create a contingency plan
R2 | Risk | Data migration errors during deployment could cause data loss | High | Low | Implement a rigorous testing protocol, including mock data migration exercises
A1 | Assumption | All stakeholders will be available for regular feedback | Medium | High | Confirm stakeholder availability in advance and establish a communication plan that accommodates their schedules
A2 | Assumption | Sufficient bandwidth and resources will be allocated by Florals for this project | Medium | Medium | Get written confirmation from Florals’ management on resource availability and commitment
I1 | Issue | Delays in requirement gathering due to stakeholder unavailability | High | Medium | Proactively engage with stakeholders to ensure timely participation
D1 | Dependency | The project depends on the availability of third-party tools and APIs | Medium | Medium | Coordinate with third-party vendors to ensure timely availability and access
D2 | Dependency | Timely sign-off on key deliverables by Florals | High | Medium | Align project milestones with the stakeholder decision-making process and escalate if delays occur

## Resource Plan
S.No | Resource Role | Allocation | Occupancy Period | Tasks Involved
1 | Project Manager | 50% for entire project duration | 01-Sep-2024 to 24-Jan-2025 | Project planning, monitoring, communication, risk management, and project closure
2 | Business Analyst | 100% during requirements phase | 07-Sep-2024 to 25-Sep-2024 | Requirement gathering, BRD preparation, validation
3 | UI/UX Designer | 100% during design phase | 23-Sep-2024 to 11-Oct-2024 | Website design, wireframes, and mockups creation
4 | Frontend Developer | 100% during development phase | 07Oct-2024 to 01-Nov-2024 | Frontend development, integration with backend
5 | Backend Developer | 100% during development phase | 28-Oct-2024 to 22-Nov-2024 | Backend development, API integration, database setup
6 | Integration Specialist | 100% during integration phase | 18-Nov-2024 to 29-Nov-2024 | System integration, legacy and third-party tools integration
7 | QA/Testers | 100% during testing phase | 01-Dec-2024 to 16-Dec-2024 | Unit testing, SIT, UAT, performance testing
8 | Data Migration Specialist | 50% during deployment phase | 22-Dec-2024 to 28-Dec-2024 | Data migration and verification

## Escalation Matrx
S.No | Governance & Escalation Matrix | Role | Name/Contact | Responsibilities | Escalation Point | Escalation Level
1 | Project Sponsor | Sponsor | [Name/Email/Phone] | Final decision-maker, approves budget and major changes, ensures alignment with business objectives | CEO/Executive Board | Level 3 (Critical Issues)
2 | Project Manager | PM | [Name/Email/Phone] | Overall project management, planning, execution, monitoring, risk management, communication | Project Sponsor | Level 2 (Major Issues)
3 | Steering Committee | SC | [Name/Email/Phone] | Strategic oversight, resolves high-level issues, reviews progress, and makes decisions on major changes | Project Sponsor | Level 3 (Critical Issues)
4 | Business Analyst | BA | [Name/Email/Phone] | Requirements gathering, BRD creation, stakeholder communication | Project Manager | Level 1 (Operational Issues)
5 | Technical Lead | TL | [Name/Email/Phone] | Leads technical development, ensures quality and adherence to standards, resolves technical issues | Project Manager | Level 2 (Major Issues)
6 | UI/UX Designer | Designer | [Name/Email/Phone] | Responsible for the design phase, creating wireframes, and ensuring user-friendly interface | Technical Lead | Level 1 (Operational Issues)
7 | Frontend Developer | Developer | [Name/Email/Phone] | Develops the frontend of the website, collaborates with backend team | Technical Lead | Level 1 (Operational Issues)
8 | Backend Developer | Developer | [Name/Email/Phone] | Develops backend systems, integrates APIs, and ensures data management | Technical Lead | Level 1 (Operational Issues)
9 | QA/Testers | Tester | [Name/Email/Phone] | Conducts testing phases, identifies bugs, ensures quality and performance standards | Technical Lead | Level 1 (Operational Issues)
10 | Integration Specialist | Specialist | [Name/Email/Phone] | Manages system integration, ensures compatibility with legacy systems and third-party tools | Technical Lead | Level 1 (Operational Issues)
11 | Data Migration Specialist | Specialist | [Name/Email/Phone] | Oversees data migration process, verifies data integrity post-migration | Technical Lead | Level 1 (Operational Issues)
12 | Support Team Lead | Support Lead | [Name/Email/Phone] | Manages post-launch support, handles user training and documentation | Project Manager | Level 2 (Major Issues)
13 | Vendor Contact (Third-Party Tools) | Vendor | [Vendor Name/Email/Phone] | Manages third-party tool integration, resolves vendor-related issues | Technical Lead | Level 2 (Vendor Issues)
14 | Customer Representative (Florals) | Customer Rep | [Name/Email/Phone] | Provides customer feedback, ensures project meets business objectives | Project Manager | Level 2 (Customer Concerns)
Escalation Levels:
| Level 1 (Operational Issues) | These are day-to-day issues that can be resolved within the project team or by a direct report to the Technical Lead.
| Level 2 (Major Issues) | These issues affect project timelines, costs, or quality and require the attention of the Project Manager or Steering Committee.
| Level 3 (Critical Issues) | Critical issues that jeopardize the success of the project or require significant changes to scope or budget should be escalated to the Project Sponsor or higher authority.

## Communication Plan
S.No | Communication Type | Objective | Audience | Frequency | Owner | Delivery Method | Key Content
1 | Kick-off Meeting | Project introduction, roles definition | Project Team, Stakeholders | Once (Project Start) | Project Manager | In-Person/Virtual Meeting | Project overview, goals, roles, timeline, deliverables
2 | Weekly Status Meeting | Update on progress, risks, and issues | Project Team | Weekly | Project Manager | Virtual Meeting/Conference Call | Progress report, risk log, issues, next steps
3 | Steering Committee Meeting | High-level project review, decision-making | Steering Committee | Bi-Weekly | Project Manager | Virtual Meeting | Status update, milestone progress, major risks, decisions
4 | Milestone Review | Review of completed milestones | Project Sponsor, Stakeholders | At Milestone Completion | Project Manager | Report/Presentation | Milestone deliverable, lessons learned, next phase readiness
5 | Monthly Progress Report | Detailed project progress report | Stakeholders, Sponsor | Monthly | Project Manager | Email/Shared Document | Summary of completed work, risks, issues, upcoming tasks
6 | Risk Review Meeting | Review and update of the risk log | Risk Management Team | Bi-Weekly | Project Manager/Risk Manager | Virtual Meeting | Updated risk log, mitigation strategies, new risks
7 | Ad-hoc Meeting | Issue resolution or urgent updates | Relevant Team Members | As needed | Project Manager | Virtual Meeting/Call | Specific issue details, action items, resolution steps
8 | Project Closure Meeting | Final review, lessons learned | Project Team, Stakeholders | Once (End of Project) | Project Manager | In-Person/Virtual Meeting | Project outcomes, success metrics, final documentation

## Reporting
S.No | Report Name | Frequency | Owner | Audience | Report Content | Format | Delivery Method
1 | Weekly Status Report | Weekly | Project Manager | Project Team | Progress against schedule, tasks completed, upcoming tasks, risks/issues, action items | Word/Excel/PDF | Email/Project Management Tool
2 | Monthly Progress Report | Monthly | Project Manager | Project Sponsor, Stakeholders | Summary of project status, milestone achievements, budget update, key risks, upcoming milestones | Word/Excel/PDF | Email/Shared Drive
3 | Milestone Report | At Milestone Completion | Project Manager | Project Sponsor, Steering Committee | Detailed summary of completed milestone, deliverables, issues faced, next steps | PowerPoint Presentation | In-Person/Virtual Meeting
4 | Risk Management Report | Bi-Weekly | Risk Manager | Risk Management Team | Updated risk log, mitigation strategies, newly identified risks, impact analysis | Excel | Email/Shared Drive
5 | Change Request Log | As Needed | Change Control Board | Project Manager | Detailed log of all change requests, their status, impact on scope, schedule, and budget | Excel | Email/Shared Drive
6 | Project Closure Report | Once (End of Project) | Project Manager | Project Sponsor, Stakeholders | Final project outcomes, budget summary, lessons learned, post-launch support plan | Word/PowerPoint | In-Person/Virtual Meeting

## Project Budget
S.No | Category | Cost Item | Description | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Personnel Costs
|  | Project Manager | Overall project management | 5 months | 10000 | 50000
|  | Business Analyst | Requirement gathering and documentation | 2 months | 8000 | 16000
|  | UI/UX Designer | Website design, wireframes, and mockups | 2 months | 7500 | 15000
|  | Frontend Developer | Frontend development | 3 months | 9000 | 27000
|  | Backend Developer | Backend development, database, API integration | 3 months | 9500 | 28500
|  | Integration Specialist | System and third-party integration | 2 months | 8500 | 17000
|  | QA/Testers | Testing and quality assurance | 2 months | 7000 | 14000
|  | Data Migration Specialist | Data migration and verification | 1 month | 8000 | 8000
|  | Support Team Lead | Post-launch support, user training | 1 month | 7000 | 7000
2 | Software Costs
|  | Design Software | UI/UX design tools | 1 package | 1500 | 1500
|  | Testing Tools | Automated testing tools | 1 package | 3000 | 3000
|  | Project Management Software | Tools for planning, tracking, and collaboration | 5 months | 1000 | 5000
3 | Hardware Costs
|  | Development Servers | For development and testing environments | 2 servers | 5000 | 10000
|  | Production Servers | For hosting the live website | 3 servers | 6000 | 18000
|  | Backup Systems | Backup and disaster recovery systems | 1 system | 4000 | 4000
4 | Miscellaneous Costs
|  | Training Materials | User training guides and materials | 100 copies | 50 | 5000
|  | Travel Expenses | Travel for meetings, training sessions | 5 trips | 1000 | 5000
|  | Contingency Fund | For unforeseen expenses | Lump sum | 10000 | 10000
5 | Total Costs |  |  |  |  | 244000